## Sheet1
Story ID | Functional | Value | Acceptance Criteria | Backlog AC | Priority | Sequence | Tasks | UI | Effort | Dependency/Discussion Pts | Design Docs | Test Cases | Start | Completed
MH1 | Launch the application by signing in | The system can identify the type of user and the user can use the main application | • On launching the application, the main application window appears • The user is able to enter the access details • The user access details are authenticated from the database. |  | Must Have | 1 | • Create a database with the name "Directory" and set it up on a local server. • Create a table "Users" with the fields "user_id", "name", "password", "privelege" and "last_login_time" for use in the database • Create a sign-in form for the user • Write a server side php script to fetch information from the database • Write asynchronous communication layer to authenticate the user details via AJAX. • Create a home page for the user to land after sign in authentication. | UI\LoginPage_failure.png | • 1 hr • 2 hr • 2 hr |  |  |  | 16/8/2015 | 20/8/2015
UI\LoginPage_success.png
| Register a new user | A new user can sign up and the administrator can grant access to the user to use the application. |  |  | Delighter | 10
MH3 | Save contact details | The user is able to save the new contact details to the database. The entered contact details are sent to the server which after validation are added into the database. | • The contact details are saved into the database on choosing the save option • If the details are invalidated, the server doesn’t add them in the database • If a duplicate contact is being added, an error message is displayed prompting the user for so • If the server is down, an appropriate error message is shown to the user |  | Must Have | 3 | • Write a server side script for validating data received to the server. • Write a server side script for inserting new details to the database. • Write a server side script for preventing duplicate details. | ..\..\..\..\Program Files\Apache Software Foundation\Tomcat 8.0\webapps\teleDirect\Design\UI\save_contact_success.PNG |  |  |  |  | 31/8/2015 | 2015-01-09
MH 4 | View list of contacts | The user is able to see all the contact in grid/list layout that are saved in the database. | • The contacts are shown in a list/grid layout to the user having the photograph and their full name. • If a new contact is added, the change is reflected in the list/grid. • If contact name is changed, the change is reflected in the list/grid. • If contact is deleted, the change is reflected in the list/grid. |  | Must Have | 4 | • Create a layout for the box elements which will contain a photo and full name • Write a script to dynamically populate the layout with box elements as required • Write a server side script to fetch the list of all contacts from the database. | [5 empty] | 2015-02-09
MH5 | View contact details | The user is able to access the details about the contact | • A new column to list of contacts shows the contact number. • If theres is no number corresponding to a contact, the number is left blank. • A dialog pops up showing the other details of the contact. • If a contact photo exists, it is shown otherwise a generic picture is displayed |  | Must Have | 5
| Call a contact | The user is able to place calls to a particular contact | • The contact number is highlighted in blue color and clickable. • On clicking the phone number, the number is dialed through a suitable application. |  | Satisfier | 16
| Email the contact | The user is able to email the contact |  |  | Delighter | 11
| Search contact | The user is able to search for a particular contact from the database |  |  | Delighter | 12
| Dynamic suggestions in search box | The system gives suggestions dynamically as the user types in the search box saving typing time. |  |  | Satisfier | 18
MH2 | Add a new contact | The user is able to enter new contact details which after validation can be added to the database. | • The use can click on an add button to create a new contact in the database • The user needs write priveleges • A blank form is shown to enter the details of the contact like name, title, contact number, email address, Home address, gender, age etc. • The default values are filled in • The entered details are validated and checked for duplication • The validated details are saved into the database on selecting the save option |  | Must have | 2 | • Create two tables namely "Contacts" and "ContactAddDetails" • The table "Contacts" contains the following fields - contact_id - title - first_name - middle_name - last_name - home_num - work_num • The table "ContactAddDetails" contains: - company - dob - email - home_address - work_address - photograph - notes • Create a homepage for the user with the add button. • Create a form in a dialog box for adding new contact details - fields in 'Contacts' are compulsory - fields in 'ContactAddDetails' are optional • Write a class for filling in default values • Write a class for client-side validation • Relay the information from the form to the server script | UI\HomePage_add_contact.PNG | • • • 1 hour • 1 hour • 1 hour • 1 hour • 2 hour • • 1 hour |  |  |  | 24/8/2015 | 28/8/2015
UI\new_contact.PNG
| Add contact photo | The user is able to add a photographic alias to associate with the contact. |  |  | Delighter | 8
MH6 | Update contact details | The user is able to make changes to the contact details as when required | • The user has write priveleges • The form appears in the edit mode and the contact details are editable • The entry fields are validated against the validation norms • The system checks for duplicate records like for name, contact number etc. • The save option is available only after all the fields are validated and no duplication found • On saving, the details are updated in the database |  | Must have | 6 | • Write a server script for updating the contact details as sent by the client • Create an update mode that would be available only to the user with edit priveleges • Enable save button only when the form is valid
| Update the contact photo | The user can change the contact photo. |  |  | Delighter | 9
| Optimize the uploaded contact photo for storage in the database | The photographs stored in the database are processed for space optimization saving storage space, data fetching time and internet bandwidth. |  |  | Satisfier | 19
| Prevent mismatch of contact title and gender | There is no conflict between title and gender. |  |  | Delighter | 13
MH7 | Delete a contact | The user is able to remove contacts from the database | • The records are selectable and can be deleted by pressing the delete key • Can also be deleted by clicking the delete button • The system asks for confirmation before deleting the contact record |  | Must have | 7
| Recover deleted contacts by mistake | Contacts deleted by mistake can be recovered |  |  | Delighter | 14
| Prompt an error if the database server is down or unavailable | Prompt user if the database is not available |  |  | Delighter | 15
| Select multiple contacts for deletion | The user can make multiple selections and make deleteions faster |  |  | Satisfier | 17